## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Requirements Analysis | 40 | 1000 | 0 | 0 | 0 | 1040
| Identify Stakeholders | 8 | 200 | 0 | 0 | 200 | 408
| Gather Website Requirements | 16 | 352 | 0 | 0 | 0 | 368
| Conduct Stakeholder Interviews | 8 | 176 | 0 | 0 | 0 | 184
| Identify Webpages Needed | 8 | 200 | 0 | 0 | 0 | 208
| Gather Visual & Branding Requirements | 10 | 250 | 0 | 0 | 0 | 260
| Define Gallery Requirements | 10 | 180 | 0 | 0 | 0 | 190
| Subtotal | 100 | 2358 | 0 | 0 | 200 | 2658
PROJECT DEVELOPMENT | Wireframes (All Tasks) | 48 | 960 | 0 | 0 | 0 | 1008
| UI Designs (All Tasks) | 24 | 480 | 0 | 0 | 0 | 504
| Style Guide | 8 | 160 | 0 | 0 | 0 | 168
| UI Development Homepage | 20 | 460 | 0 | 0 | 0 | 480
| UI Development Gallery | 20 | 460 | 0 | 0 | 0 | 480
| UI Development Contact Page | 20 | 460 | 0 | 0 | 0 | 480
| Integrate Sample Photos | 10 | 230 | 0 | 0 | 0 | 240
| Subtotal | 150 | 3210 | 0 | 0 | 0 | 3360
PROJECT DELIVERY | Testing (UI Testing) | 16 | 288 | 0 | 0 | 0 | 304
| Fix Bugs & Layout Issues | 24 | 552 | 0 | 0 | 0 | 576
| Deployment | 16 | 400 | 0 | 0 | 0 | 416
| Final Deployment | 8 | 200 | 0 | 0 | 0 | 208
| Subtotal | 64 | 1440 | 0 | 0 | 0 | 1504
PROJECT MANAGEMENT | Customer Progress Meetings | 10 | 250 | 0 | 0 | 0 | 260
| Internal Status Meetings | 10 | 250 | 0 | 0 | 0 | 260
| Vendor Cordination | 5 | 125 | 0 | 0 | 0 | 130
| Project Oversight | 10 | 250 | 0 | 0 | 0 | 260
| Quality Assurance Oversight | 5 | 90 | 0 | 0 | 0 | 95
| Configuration Management | 5 | 125 | 0 | 0 | 0 | 130
| Subtotal | 45 | 1090 | 0 | 0 | 0 | 1135
OTHER COST | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0
Subtotals |  | 359 | 8098 | 0 | 0 | 200 | 8657
Risk (Contingency) |  | 0 | 0 | 0 | 0 | 0 | 0
Total (Scheduled) |  | 359 | 8098 | 0 | 0 | 200 | 8657

## Expenditures Over Time
Expenditures Over Time
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PLANNING (RFP) | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PLANNING 2 | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| CONSTRUCTION | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| TEST & DELIVERY | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PROJECT TOTAL |  | 0

## Cumulative Project Costs
Projected vs. Actual Costs
MONTHLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| MONTH | PROJECTED MONTHLY COST | ACTUAL MONTHLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 1940 | 1610 | 2360 | 2750
| 2 | 1480 | 3190 | 1490 | 2950
| 3 | 1390 | 1930 | 1720 | 2510
| 4 | 4030 | 1370 | 1590 | 2330
| 5 | 3640 | 3680 | 4040 | 3650
| 6 | 2480 | 1180 | 3430 | 1840
| 7 | 3040 | 2390 | 1700 | 1660
| 8 | 2160 | 4040 | 3330 | 3300
| 9 | 1600 | 1330 | 1050 | 2980
| 10 | 2300 | 1140 | 2450 | 2990
| 11 | 3070 | 4210 | 3620 | 3540
| 12 | 2300 | 3910 | 1330 | 2230
| 13 | 1920 | 1580 | 4210 | 3910
| 14 | 3140 | 3850 | 1580 | 1500
| 15 | 2850 | 4000 | 3520 | 3020
| 16 | 2060 | 3700 | 1320 | 2590
| 17 | 1760 | 2900 | 3220 | 2990
| 18 | 3740 | 1870 | 3480 | 3660
| 19 | 3670 | 2180 | 3980 | 1230
| 20 | 3230 | 2790 | 3710 | 2190
| 21 | 2140 | 2550 | 1550 | 1940
| 22 | 1260 | 3890 | 2620 | 2470
| 23 | 3750 | 1850 | 2490 | 2170
| 24 | 2880 | 1740 | 2220 | 2140